## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G TDD |  | NHM016 | 543216 | Nabeul | B5G4G_Hammamet_LGD | 5G_Hammamet_LGD_N78_1 | 781 | 605 | 2 | NHM016R | 647328 |  | 100MHZ | CELL_BW_100M | 30 | 123 | 5000 | 4 | 120 | 36.3965 | 10.614 | 125 |  |  |  |  | Nabeul
5G TDD |  | NHM016 | 543216 | Nabeul | B5G4G_Hammamet_LGD | 5G_Hammamet_LGD_N78_2 | 782 | 605 | 2 | NHM016S | 647328 |  | 100MHZ | CELL_BW_100M | 30 | 124 | 5000 | 5 | 120 | 36.3965 | 10.614 | 340 |  |  |  |  | Nabeul

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Hammamet_LGD |  | Site Name(*)
Test Date:17/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_100M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.614 |  |  |  | Planning
LaT |  | 36.3965 |  |  |  | Planning
Antenna Type | [5 empty] | Planning
Antenna Quantity | [5 empty] | Planning
Azimuth |  | 125 | 340 |  |  | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency |  | 647328 | 647328 |  |  | NA
PCI |  | 123 | 124 |  |  | NA
SgNB Add (OK/NOK) |  | OK | OK |  |  | NA
NR Session Setup Success Rate |  | 100 | 100 |  |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 |  |  | 100% | Pass
SgNB Add SR |  | 100 | 100 |  |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 1032.9535 | 965.4819 |  |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 818.9723 | 790.927 |  |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 107.1439 | 90.1275 |  |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 62.038 | 59.9717 |  |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 26.5 | 25.5 |  |  | 30ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -98.3654 | -98.3654 | -98.3654 | -98.3654 | NA
Av SSB RSRQ (dB) |  | -11.0184 | -11.0184 | -11.0184 | -11.0184 | NA
Av SSB-SINR (dB) |  | 18.0351 | 18.0351 | 18.0351 | 18.0351 | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 59.25 | 59.25 | 59.25 | 59.25 | NA
SgNB Abnormal Release Rate |  | 0% | 0% | 0% | 0% | 0% | Pass
Pscell Change Success Rate |  | 100% | 100% | 100% | 100% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 640.1677 | 640.1677 | 640.1677 | 640.1677 | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 462.02 | 462.02 | 462.02 | 462.02 | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 74.8082 | 74.8082 | 74.8082 | 74.8082 | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 54.6103 | 54.6103 | 54.6103 | 54.6103 | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Site Photos
Sector 1 | Sector 2
Sector 3 | Sector 4

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 1032.9535 | 965.4819
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 818.9723 | 790.927
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 107.1439 | 90.1275
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 62.038 | 59.9717
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 1394.1863 | 1230.741
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 1266.2579 | 960.8592
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 124.2143 | 117.3027
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 83.5639 | 65.0304