## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Longitude | Latitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G TDD |  | LHM019 | 542019 | Nabeul | 5G_Imm_Ben_Romdhane | 5G_Imm_Ben_Romdhane_N78_1 | 31 | 605 | 2 | NHM019R | 647332 | 31 | 100MHZ | CELL_BW_10M | 30 | 153 | 15000 | 7 |  | 10.62408736 | 36.4022395 | 60 |  |  |  |  | Nabeul
5G TDD |  | LHM019 | 542019 | Nabeul | 5G_Imm_Ben_Romdhane | 5G_Imm_Ben_Romdhane_N78_2 | 32 | 605 | 2 | NHM019S | 647332 | 32 | 100MHZ | CELL_BW_10M | 30 | 154 | 15000 | 8 |  | 10.62408736 | 36.4022395 | 180 |  |  |  |  | Nabeul
5G TDD |  | LHM019 | 542019 | Nabeul | 5G_Imm_Ben_Romdhane | 5G_Imm_Ben_Romdhane_N78_3 | 33 | 605 | 2 | NHM019T | 647332 | 33 | 100MHZ | CELL_BW_10M | 30 | 155 | 15000 | 9 |  | 10.62408736 | 36.4022395 | 300 |  |  |  |  | Nabeul

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 973.2155 | 871.2815 | 1009.0015
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 765.6246 | 760.263 | 777.2854
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 96.4149 | 100.7159 | 88.9037
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 66.9797 | 62.9768 | 60.8626
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 1233.5494 | 1112.9177 | 1394.5095
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 936.9346 | 956.3614 | 953.3008
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 177.5021 | 125.7141 | 114.2765
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 101.2042 | 82.5654 | 69.371

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Imm_Ben_Romdhane |  | Site Name(*)
Test Date:06/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.62408736 |  |  |  | Planning
LaT |  | 36.4022395 |  |  |  | Planning
Antenna Type | [5 empty] | Planning
Antenna Quantity | [5 empty] | Planning
Azimuth |  | 60 | 180 | 300 |  | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency | [5 empty] | NA
PCI |  | 78 | 79 | 80 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 973.2155 | 871.2815 | 1009.0015 |  | 750 Mbps/200Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 765.6246 | 760.263 | 777.2854 |  | 650 Mbps/60Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 96.4149 | 100.7159 | 88.9037 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 66.9797 | 62.9768 | 60.8626 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 26.5 | 34.5 | 19 |  | 30ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -82 |  |  |  | NA
Av SSB RSRQ (dB) |  | -10 |  |  |  | NA
Av SSB-SINR (dB) |  | 18 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 55.875 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% | 0% | 0% | 0% | 0% | Pass
Pscell Change Success Rate |  | 100% | 100% | 100% | 100% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 925.0808 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 805.6891 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 101.9314 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 83.2702 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Site Photos
Sector 1 | Sector 2
Sector 3 | Sector 4

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL