## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Longitude | Latitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G FDD |  | LHM006 | 542006 | Nabeul | Shalimar | 5G_Shalimar_N3_1 | 31 | 605 | 2 | LHM006X | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 63 | 15000 | 30 |  | 10.55216439 | 36.38771953 | 50 |  |  |  |  | Nabeul
5G FDD |  | LHM006 | 542007 | Nabeul | Shalimar | 5G_Shalimar_N3_2 | 32 | 605 | 2 | LHM006Y | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 64 | 15000 | 40 |  | 10.55216439 | 36.38771953 | 210 |  |  |  |  | Nabeul
5G FDD |  | LHM006 | 542008 | Nabeul | Shalimar | 5G_Shalimar_N3_3 | 33 | 605 | 2 | LHM006Z | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 65 | 15000 | 50 |  | 10.55216439 | 36.38771953 | 310 |  |  |  |  | Nabeul

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 208.1875 | 205.258 | 216.9287
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 113.3643 | 108.3257 | 110.8662
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 66.9996 | 51.7276 | 63.1238
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 30.1507 | 22.2035 | 26.7138
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 495.4709 | 307.1928 | 329.3234
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 154.3696 | 145.0117 | 143.4991
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 80.7114 | 108.2226 | 86.0342
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 37.5766 | 33.5109 | 37.1847

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Shalimar |  | Site Name(*)
Test Date:07/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.55216439 |  |  |  | Planning
LaT |  | 36.38771953 |  |  |  | Planning
Antenna Type | [5 empty] | Planning
Antenna Quantity | [5 empty] | Planning
Azimuth |  | 50 | 210 | 310 |  | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency | [5 empty] | NA
PCI |  | 219 | 220 | 221 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 208.1875 | 205.258 | 216.9287 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 113.3643 | 108.3257 | 110.8662 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 66.9996 | 51.7276 | 63.1238 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 30.1507 | 22.2035 | 26.7138 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 26.75 | 32 | 31.33 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -80 |  |  |  | NA
Av SSB RSRQ (dB) |  | -11 |  |  |  | NA
Av SSB-SINR (dB) |  | 15 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 59.75 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% | 0% | 0% | 0% | 0% | Pass
Pscell Change Success Rate |  | 100% | 100% | 100% | 100% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 224.57 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 115.8245 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 63.868 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 25.993 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Site Photos
Sector 1 | Sector 2
Sector 3 | Sector 4

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput
NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL