## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G TDD |  | NSO250 | 5494350 | Sousse | 5G_Msaken_5 | 5G_Msaken_5_N3_1 |  | 605 | 2 | NSO250X | 647332 |  | 100MHZ | CELL_BW_100M | 30 | 816 | 5000 | 453 | 130 | 35.7279 | 10.593 | 110 |  |  |  |  | Sousse
5G TDD |  | NSO250 | 5494350 | Sousse | 5G_Msaken_5 | 5G_Msaken_5_N3_2 |  | 605 | 2 | NSO250Y | 647332 |  | 100MHZ | CELL_BW_100M | 30 | 817 | 5000 | 463 | 130 | 35.7279 | 10.593 | 220 |  |  |  |  | Sousse
5G TDD |  | NSO250 | 5494350 | Sousse | 5G_Msaken_5 | 5G_Msaken_5_N3_3 |  | 605 | 2 | NSO250Z | 647332 |  | 100MHZ | CELL_BW_100M | 30 | 818 | 5000 | 473 | 130 | 35.7279 | 10.593 | 310 |  |  |  |  | Sousse

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Msaken_5 |  | Site Name(*)
Test Date:27/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_100M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.593 |  |  |  | Planning
LaT |  | 35.7279 |  |  |  | Planning
Antenna Type |  |  |  |  | - | Planning
Antenna Quantity |  |  |  |  | - | Planning
Azimuth |  | 110 | 220 | 310 | - | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency |  | 647332 | 647332 | 647332 |  | NA
PCI |  | 816 | 817 | 818 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 1547.3217 | 1041.3959 | 905.5879 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 1239.2973 | 818.6002 | 789.1542 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 113.4961 | 104.2068 | 104.92 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 63.155 | 64.7203 | 61.75 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 25.5 | 28.5 | 29.5 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -87 |  |  |  | NA
Av SSB RSRQ (dB) |  | -10 |  |  |  | NA
Av SSB-SINR (dB) |  | 17 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 59.71 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% |  |  |  | 0% | Pass
Pscell Change Success Rate |  | 100% | 93.33% | 93.33% | 93.33% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 907.577 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 737.2404 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 78.8221 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 54.4265 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 1547.3217 | 1041.3959 | 905.5879
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 1239.2973 | 818.6002 | 789.1542
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 113.4961 | 104.2068 | 104.92
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 63.155 | 64.7203 | 61.75
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 1988.0906 | 1395.6861 | 1156.1563
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 1531.5043 | 973.406 | 947.3797
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 143.5272 | 131.1069 | 234.46
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 81.1648 | 79.8171 | 82.78

## OSS KPI
KPI | Threshold | Week_14
EN_DC_SETUP_succ_RATE_gNB (%) | 99 | 97.9467
EN_DC_SETUP_succ_RATE_eNB (%) | 99 | 97.3405
EN_DC_intra_sgNB_PSCell_Change_succ_rate (%) | 99 | 100
EN_DC_inter_sgNB_PSCell_Change_succ_rate (%) | 98 | 36.6791
SCG_Radio_Resource_Retainability_Act (%) | 1 | 0.37891
SCG_Radio_Resource_Retainability_origin_gNb_Act (%) | 0.5 | 0.15313
Diff_Init_E-Rab_Establish_Succ_Rate (%) | 99 | 99.9719
Diff_E-RAB_Retainability (%) | 0.5 | 0.11164
Diff_Cell_Mobility_Succ_Rate_LTE (%) | 98 | 99.8065