## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G FDD |  | NSO248 | 544348 | Sousse | 5G_Taffala | 5G_Taffala_N3_1 | 31 | 605 | 2 | NSO248X | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 966 | 5000 | 423 | 130 | 35.8104 | 10.636 | 130 |  |  |  |  | Sousse
5G FDD |  | NSO248 | 544348 | Sousse | 5G_Taffala | 5G_Taffala_N3_2 | 32 | 605 | 2 | NSO248Y | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 967 | 5000 | 433 | 130 | 35.8104 | 10.636 | 235 |  |  |  |  | Sousse
5G FDD |  | NSO248 | 544348 | Sousse | 5G_Taffala | 5G_Taffala_N3_3 | 33 | 605 | 2 | NSO248Z | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 968 | 5000 | 443 | 130 | 35.8104 | 10.636 | 330 |  |  |  |  | Sousse

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Taffala |  | Site Name(*)
Test Date:17/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.636 |  |  |  | Planning
LaT |  | 35.8104 |  |  |  | Planning
Antenna Type |  |  |  |  | - | Planning
Antenna Quantity |  |  |  |  | - | Planning
Azimuth |  | 130 | 235 | 330 | - | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency |  | 362000 | 362000 | 362000 |  | NA
PCI |  | 966 | 967 | 968 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 153.4198 | 158.3891 | 298.0305 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 82.665 | 110.8562 | 88.1866 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 54.2906 | 79.9277 | 49.4526 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 19.1869 | 35.911 | 21.1281 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 23.5 | 26.5 | 27.5 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -76 |  |  |  | NA
Av SSB RSRQ (dB) |  | -11 |  |  |  | NA
Av SSB-SINR (dB) |  | 9 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 110 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% |  |  |  | 0% | Pass
Pscell Change Success Rate |  | 100% | 93.33% | 93.33% | 93.33% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 161.1168 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 115.0636 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 57.5574 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 30.7626 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 153.4198 | 158.3891 | 298.0305
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 82.665 | 110.8562 | 88.1866
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 54.2906 | 79.9277 | 49.4526
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 19.1869 | 35.911 | 21.1281
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 274.9736 | 406.7328 | 849.1561
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 109.9224 | 137.0857 | 142.6314
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 82.6026 | 95.3038 | 83.5004
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 35.4657 | 42.6591 | 26.7664

## OSS KPI
KPI | Threshold | Week_14
EN_DC_SETUP_succ_RATE_gNB (%) | 99 | 99.7833
EN_DC_SETUP_succ_RATE_eNB (%) | 99 | 99.7266
EN_DC_intra_sgNB_PSCell_Change_succ_rate (%) | 99 | 100
EN_DC_inter_sgNB_PSCell_Change_succ_rate (%) | 98 | 99.1622
SCG_Radio_Resource_Retainability_Act (%) | 1 | 0.5032
SCG_Radio_Resource_Retainability_origin_gNb_Act (%) | 0.5 | 0.12051
Diff_Init_E-Rab_Establish_Succ_Rate (%) | 99 | 99.9831
Diff_E-RAB_Retainability (%) | 0.5 | 0.095996
Diff_Cell_Mobility_Succ_Rate_LTE (%) | 98 | 99.8098