## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G FDD |  | NSO045 | 541345 | Sousse | 5G_Tahar_Sfar | 5G_Tahar_Sfar_N3_1 | 31 | 605 | 2 | NSO045X | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 126 | 5000 | 722 | 130 | 35.8314 | 10.6329 | 110 |  |  |  |  | Sousse
5G FDD |  | NSO045 | 541345 | Sousse | 5G_Tahar_Sfar | 5G_Tahar_Sfar_N3_2 | 32 | 605 | 2 | NSO045Y | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 127 | 5000 | 732 | 130 | 35.8314 | 10.6329 | 220 |  |  |  |  | Sousse
5G FDD |  | NSO045 | 541345 | Sousse | 5G_Tahar_Sfar | 5G_Tahar_Sfar_N3_3 | 33 | 605 | 2 | NSO045Z | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 128 | 5000 | 742 | 130 | 35.8314 | 10.6329 | 325 |  |  |  |  | Sousse

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:Tahar_Sfar |  | Site Name(*)
Test Date:18/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.6329 |  |  |  | Planning
LaT |  | 35.8314 |  |  |  | Planning
Antenna Type |  |  |  |  | - | Planning
Antenna Quantity |  |  |  |  | - | Planning
Azimuth |  | 110 | 220 | 325 | - | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency |  | 362000 | 362000 | 362000 |  | NA
PCI |  | 126 | 127 | 128 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 217.0966 | 140.2186 | 140.6923 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 108.6085 | 107.6396 | 90.4307 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 48.8922 | 46.5265 | 46.5976 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 21.4848 | 29.0117 | 20.7774 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 26.5 | 26.5 | 30.5 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -87 |  |  |  | NA
Av SSB RSRQ (dB) |  | -11 |  |  |  | NA
Av SSB-SINR (dB) |  | 9 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 57.13 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% |  |  |  | 0% | Pass
Pscell Change Success Rate |  | 100% | 93.33% | 93.33% | 93.33% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 246.3267 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 191.8129 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 41.359 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 24.303 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 217.0966 | 140.2186 | 140.6923
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 108.6085 | 107.6396 | 90.4307
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 48.8922 | 46.5265 | 46.5976
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 21.4848 | 29.0117 | 20.7774
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 265.827 | 256.2136 | 257.7129
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 164.901 | 170.6971 | 142.4956
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 64.9082 | 68.7156 | 55.2427
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 30.4553 | 37.475 | 28.1481

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL

## OSS KPI
KPI | Threshold | Week_14
EN_DC_SETUP_succ_RATE_gNB (%) | 99 | 99.7672
EN_DC_SETUP_succ_RATE_eNB (%) | 99 | 99.7182
EN_DC_intra_sgNB_PSCell_Change_succ_rate (%) | 99 | 99.9801
EN_DC_inter_sgNB_PSCell_Change_succ_rate (%) | 98 | 99.445
SCG_Radio_Resource_Retainability_Act (%) | 1 | 1.0889
SCG_Radio_Resource_Retainability_origin_gNb_Act (%) | 0.5 | 0.091285
Diff_Init_E-Rab_Establish_Succ_Rate (%) | 99 | 99.9899
Diff_E-RAB_Retainability (%) | 0.5 | 0.066028
Diff_Cell_Mobility_Succ_Rate_LTE (%) | 98 | 99.65