## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G FDD |  | NSO011 | 541311 | Sousse | 5G_El_Kantaoui_EV | 5G_El_Kantaoui_EV_N3_1 | 31 | 605 | 2 | NSO011X | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 6 | 5000 | 2 | 130 | 35.8952 | 10.5903 | 70 |  |  |  |  | Sousse
5G FDD |  | NSO011 | 541311 | Sousse | 5G_El_Kantaoui_EV | 5G_El_Kantaoui_EV_N3_2 | 32 | 605 | 2 | NSO011Y | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 7 | 5000 | 12 | 130 | 35.8952 | 10.5903 | 250 |  |  |  |  | Sousse
5G FDD |  | NSO011 | 541311 | Sousse | 5G_El_Kantaoui_EV | 5G_El_Kantaoui_EV_N3_3 | 33 | 605 | 2 | NSO011Z | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 8 | 5000 | 22 | 130 | 35.8952 | 10.5903 | 360 |  |  |  |  | Sousse

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 195.0663 | 175.96 | 181.755
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 90.4548 | 79.6113 | 81.5544
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 80.327 | 79.3119 | 40.0709
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 35.37 | 32.3034 | 17.7192
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 412.8394 | 346.1968 | 304.0329
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 126.9422 | 112.9606 | 110.0561
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 100.8363 | 181.4446 | 58.5334
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 43.5678 | 42.3784 | 26.8591

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:El_Kantaoui_EV |  | Site Name(*)
Test Date:25/03/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks | Wrong Azimuth
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass |  | DB | Field
FTP Service |  | OK |  |  |  | OK | Pass |  | 70 | 0
Http Service |  | OK |  |  |  | OK | Pass |  | 250 | 70
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks | 360 | 250
Lon |  | 10.5903 |  |  |  | Planning
LaT |  | 35.8952 |  |  |  | Planning
Antenna Type |  |  |  |  | - | Planning
Antenna Quantity |  |  |  |  | - | Planning
Azimuth |  | 70 | 250 | 360 | - | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency | [5 empty] | NA
PCI |  | 15 | 16 | 17 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 195.0663 | 175.96 | 181.755 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 90.4548 | 79.6113 | 81.5544 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 80.327 | 79.3119 | 40.0709 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 35.37 | 32.3034 | 17.7192 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 28.5 | 25 | 25.5 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -89 |  |  |  | NA
Av SSB RSRQ (dB) |  | -11 |  |  |  | NA
Av SSB-SINR (dB) |  | 12 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 58.50 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% | 5.882% | 5.882% | 5.882% | 0% | Pass
Pscell Change Success Rate |  | 100% | 93.33% | 93.33% | 93.33% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 123.2353 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 64.7831 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 34.0988 | 34.0988 | 34.0988 | 34.0988 | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 13.0963 | 13.0963 | 13.0963 | 13.0963 | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Site Photos
Sector 1 | Sector 2
Sector 3 | Sector 4

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL