## Cell info
Scope | Date | Site ID-1 | Site ID(*) | Region | Site Name(*) | Cell Name(*) | Cell ID(*) | MCC | MNC | Transceiver Name | DlEarfcn(*) | Local Cell ID-1 | Frequency Band(*) | *Downlink bandwidth-1 | subCarrierSpacing | PCI | Radius(m) | MinRootSequenceIndex | TAC-1 | Latitude | Longitude | Azimuth(*) | Height-1 | M-Tilt-1 | E-Tilt-1 | Transceiver Comments | City-1
5G FDD |  | NSO057 | 541057 | Sousse | 5G_HAM_SOUSSE_III | 5G_HAM_SOUSSE_III_N3_1 | 31 | 605 | 2 | NSO057X | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 996 | 5000 |  | 130 | 35.8616793953088 | 10.6031393967009 | 195 |  |  |  |  | Sousse
5G FDD |  | NSO057 | 541057 | Sousse | 5G_HAM_SOUSSE_III | 5G_HAM_SOUSSE_III_N3_2 | 32 | 605 | 2 | NSO057Y | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 997 | 5000 |  | 130 | 35.8616793953088 | 10.6031393967009 | 90 |  |  |  |  | Sousse
5G FDD |  | NSO057 | 541057 | Sousse | 5G_HAM_SOUSSE_III | 5G_HAM_SOUSSE_III_N3_3 | 33 | 605 | 2 | NSO057Z | 362000 |  | 10MHZ | CELL_BW_10M | 15 | 998 | 5000 |  | 130 | 35.8616793953088 | 10.6031393967009 | 280 |  |  |  |  | Sousse

## Throughput table
Static test Throughput | SectorA | SectorB | SectorC
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 157.0251 | 141.6743 | 143.4226
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 79.8297 | 80.188 | 79.1999
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 76.614 | 48.039 | 51.128
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 31.274 | 18.58 | 27.546
Peak DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 323.3811 | 679.2911 | 362.841
Peak DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 96.5683 | 95.815 | 96.8917
Peak UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) | 89.8299 | 60.4954 | 104.0483
Peak User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) | 40.9249 | 32.5913 | 34.2249

## Main tests
Site Checklist
Site ID: |  | Site ID-1 |  | Site Name:HAM_SOUSSE_III |  | Site Name(*)
Test Date:03/04/2025 |  |  |  | Site On Air Date:
Action |  | Check |  |  |  | Threshold | Result | Remarks
The antennas whether are blocked by other antennas |  | NO |  |  |  | NO | Pass
The PCI to confirm feeder cross connection or not |  | NO |  |  |  | NO | Pass
Site Frequency BandWidth |  | CELL_BW_10M |  |  |  | NA | Pass
Service check |  | Check |  |  |  | Threshold | Result | Remarks
Intra-NR Site Handover between adjacent sectors |  | OK |  |  |  | OK | Pass
FTP Service |  | OK |  |  |  | OK | Pass
Http Service |  | OK |  |  |  | OK | Pass
Physical Information Audit |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Lon |  | 10.6031393967009 |  |  |  | Planning
LaT |  | 35.8616793953088 |  |  |  | Planning
Antenna Type |  |  |  |  | - | Planning
Antenna Quantity |  |  |  |  | - | Planning
Azimuth |  | 195 | 90 | 280 | - | Planning
D-Tilt |  |  |  |  | - | Planning
M-Tilt |  |  |  |  | - | Planning
Total Tilt |  |  |  |  | - | Planning
Antenna Height |  |  |  |  | - | Planning
Availablity |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Availablity NR |  | 100% | 100% | 100% |  | 100% | Pass
Stationary Test |  | SectorA | SectorB | SectorC | SectorD | Threshold | Result | Remarks
Frequency |  | 362000 | 362000 | 362000 |  | NA
PCI |  | 996 | 997 | 998 |  | NA
SgNB Add (OK/NOK) |  | OK | OK | OK |  | NA
NR Session Setup Success Rate |  | 100 | 100 | 100 |  | 100% | Pass
CSFB to 3G success rate(5 Attempts)(O/T) |  | 100 | 100 | 100 |  | 100% | Pass
SgNB Add SR |  | 100 | 100 | 100 |  | 100% | Pass
av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 157.0251 | 141.6743 | 143.4226 |  | 850 Mbps/140Mbps | Pass
av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 79.8297 | 80.188 | 79.1999 |  | 750 Mbps/40Mbps | Pass
av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 76.6142 | 48.0387 | 51.1285 |  | 80 Mbps/30 Mbps | Pass
av User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 31.2737 | 18.5803 | 27.5462 |  | 60 Mbps/15 Mbps | Pass
Ping 32byte Time(ms) UU Interface |  | 29.8333 | 27.5 | 30.5 |  | 40ms | Pass
Drive Test KPIs |  | Value |  |  |  | Threshold | Result | Remarks
Intra Frequency Handover success (S1->S2) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S2->S3) |  | OK |  |  |  |  | Pass
Intra Frequency Handover success (S3->S1) |  | OK |  |  |  |  | Pass
Av SSB RSRP (dBm) |  | -77 |  |  |  | NA
Av SSB RSRQ (dB) |  | -11 |  |  |  | NA
Av SSB-SINR (dB) |  | 11 |  |  |  | NA
SgNB Add SR |  | 100% | 100% | 100% | 100% | 100% | Pass
SgNB Modification interruption time (ms) (Pscell change time) |  | 59.71 |  |  |  | NA
SgNB Abnormal Release Rate |  | 0% |  |  |  | 0% | Pass
Pscell Change Success Rate |  | 100% | 93.33% | 93.33% | 93.33% | 100% | Pass
MeNB change Success Rate (Anchoring change) |  | 100% | 100% | 100% | 100% | 100% | Pass
Av DL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 113.1797 |  |  |  | NA
Av DL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 66.7527 |  |  |  | NA
Av UL User Throughput (Total) 100MHz(TDD)/10Mhz(FDD) |  | 57.8421 |  |  |  | NA
Av UL User Throughput (SCG) 100MHz(TDD)/10Mhz(FDD) |  | 32.5997 |  |  |  | NA
Acceptance |  | Total KPI Count |  |  |  | Pass |  | Remarks
Overall

## Site Photos
Sector 1 | Sector 2
Sector 3 | Sector 4

## DT NR Plots
NR PCI | NR SS-RSRP | NR SS-RSRQ
NR SS-SINR | NR DL Throughput | NR MULTI RAT DL Throughput
NR RI | Serving Cell NR ARFCN DL | NR MODULATION
NR UL Throughput | Tx power PUSCH plot | Beam Index plot DL