## 2G3G_Mtir_Maoual
|  |  | Nabeul |  | Mtir_Haoual |  |  | 2022-08-12
A-Design And Network Check
Sector | LATITUDE | LONGITUDE | AZIMUTH | HBA | Trans (FO/FH) | M-TILT | VSWR | Swapped Feeders | RET
A | 36.3988 | 10.6177 | 60 | 13.5 | FO | 0 | NO | NO | OK
B | 36.3988 | 10.6177 | 180 | 13.5 | FO | 0 | NO | NO | OK
C | 36.3988 | 10.6177 | 300 | 13.5 | FO | 0 | NO | NO | OK
2G Cell ID |  | BSC Name | CI | lac | BSIC | BCCH
32MTIRA |  | BNABEVO | 32541 | 90 | 73 | 8
32MTIRB |  | BNABEVO | 32542 | 90 | 30 | 6
32MTIRC |  | BNABEVO | 32543 | 90 | 45 | 3
3G UtranCell |  | RNC Name | Cid |  | lac/rac | UARFCN DL | PSC
UHM054X/UHM054U/UHM054O |  | NABERC1 | 20541/20544/32547 |  | 120/120 | 10713/10738/3024 | 341/341/341
UHM054Y/UHM054V/UHM054P |  | NABERC1 | 20542/20545/32548 |  | 120/120 | 10713/10738/3024 | 349/349/349
UHM054Z/UHM054W/UHM054Q |  | NABERC1 | 20543/20546/32549 |  | 120/120 | 10713/10738/3024 | 357/357/357
B-Static Check
Static Test(2G/3G) |  |  | Target |  | Sector A | Sector B | Sector C | Results(OK/NOK)
3G AMR originated call |  |  | 1 Time Successuful |  | OK | OK | OK | OK
3G AMR terminated call |  |  | 1 Time Successuful |  | OK | OK | OK | OK
Average HSDPA THPT in SC ( FTP downlaod) |  |  | 1*100MB Successful>6Mbps |  | 6.6/7.1 | 7.9/8.5 | 8/6.7 | OK
Average DC HSPDA THPT in case MC U2100 ( FTP downlaod) |  |  | 1*500MB Successful>10Mbps |  | 13.8 | 18.4 | 13.9 | OK
Average HSUPA THPT (FTP Upload) |  |  | 1*10MB Successful>2Mbps |  | 2.5/3.1 | 3.6/3.9 | 3.2/3.4 | OK
3G Web Browsing (MosaiqueFm,google,Facebook) |  |  | 1 Time Successuful |  | OK | OK | OK | OK
3G Video Streaming (sequence 2min Youtube) |  |  | 1 Time Successuful |  | OK | OK | OK | OK
2G AMR originated call |  |  | 1 Time Successuful |  | OK | OK | OK | OK
2G AMR Terminated call |  |  | 1 Time Successuful |  | OK | OK | OK | OK
C-Dynamic Check
2G/3G KPIs Drive Test |  |  | Results(OK/NOK) |  | D-OSS KPIs & Configuration check |  | Results(OK/NOK)
FTP HSUPA/HSDPA THROUGHPUT | FTP HSUPA/HSDPA THROUGHPUT | FTP HSUPA/HSDPA THROUGHPUT |  |  | 2G3G Parameters Setting
MULTIRAB TEST 3G | MULTIRAB TEST 3G | MULTIRAB TEST 3G |  |  | 4G OSS KPIs
3G RSCP during CS CALL | 3G RSCP during CS CALL | 3G RSCP during CS CALL |  |  | 2G/3G OSS KPIs (Before/After)
3G EcNo during CS CALL | 3G EcNo during CS CALL | 3G EcNo during CS CALL
2G RxLev during CS CALL | 2G RxLev during CS CALL | 2G RxLev during CS CALL
2G RXQUAL DURING CS CALL | 2G RXQUAL DURING CS CALL | 2G RXQUAL DURING CS CALL
HANDOVER | HANDOVER | HANDOVER
Comments :
SSV Validated Signature:
TT Optim Team |  |  | Date |  | Ericsson |  |  | Date

## 2G3G SSV DT PLOT
2G3G SSV REPORT
RSCP U2100 Plot | RSCP U900 Plot
EcNo U2100 Plot | EcNo U900 Plot
Best Server PSC Distribution U2100 Plot | Best Server PSC Distribution U900 Plot
DL THROUGHPUT U2100 Plot | DL THROUGHPUT U900 Plot
UL THROUGHPUT U2100 Plot | UL THROUGHPUT U900 Plot
RxLev GSM | RxQual GSM
Comments :

## 4G_MTIR_HAOUEL
LTE SSV REPORT
|  |  | Region |  | LTE Site Name |  |  | SSV Test Date
|  |  | Nabeul |  | 4G_MTIR_HAOUEL |  |  | 2022-08-12
A-Design And Network Check
Cell ID |  | TAC | PCI | Band | BW(MHZ) | Azimuth | X | Y | DL EARFCN
LHM054X/LHM054A/LHM054O |  | 120/120/120 | 150/150/150 | 1800/2100/800 | 20/10/10 | 60 | 36.3988 | 10.6177 | 1350/251/6200
LHM054Y/LHM054B/LHM054P |  | 120/120/120 | 151/151/151 | 1800/2100/800 | 20/10/10 | 180 | 36.3988 | 10.6177 | 1350/251/6200
LHM054Z/LHM054C/LHM054Q |  | 120/120/120 | 152/152/152 | 1800/2100/800 | 20/10/10 | 300 | 36.3988 | 10.6177 | 1350/251/6200
Coverage Test | Cell ID Check | TAC Check | PCI Check | Swapped Feeders | VSWR | RET
Sector A | OK | OK | OK | NO | NO | OK
Sector B | OK | OK | OK | NO | NO | OK
Sector C | OK | OK | OK | NO | NO | OK
B-Static Check
Static Test(L800/L1800/L2100) |  |  |  | Target | Sector A | Sector B | Sector C | Results(OK/NOK)
Attach Success (1 Time) |  |  |  | 100% | ok | ok | ok | ok
Attach Time (ms) (1 Time) |  |  |  | 1s | 495/512/508 | 505/560/542 | 570/611/580 | ok
Data Service Accessibility |  |  |  | 100% | ok | ok | ok | ok
Successful Download (Google,Facebook,Moasaique Fm) (1 Time) |  |  |  | 100% | ok | ok | ok | ok
Successful Download (Youtube) ( 1 Time) |  |  |  | 100% | ok | ok | ok | ok
Ping Delay (32 Bytes)(3 Times Average) |  |  |  | 50 ms | 32/40/43 | 33/43/45 | 36/46/41 | ok
Average UL/DL Throughput (Mbps)(10 MHz)(1 Time) L800 2T2R |  |  |  | 15/40 | 17.8/42.3 | 19.5/43.6 | 18.8/47.1 | ok
Average UL/DL Throughput (Mbps)(10 MHz)(1 Time) L2100 4T4R |  |  |  | 15/60 | 18.7/60.9 | 21.8/65 | 22/63.8 | ok
Average UL/DL Throughput (Mbps)(10 MHz)(1 Time) L1800 4T4R |  |  |  | 25/120 | 27.2/140.3 | 28.3/142.8 | 29.3/144.7 | ok
Average UL/DL Throughput (Mbps)(CA 40 MHz)(1 Time) 3CC |  |  |  | 25/220 | 33.5/221.6 | 30.3/223.7 | 29.1/227.4 | ok
Voice Service Accessibility Csfb (3 Times) |  |  |  | 100% | ok | ok | ok | ok
Csfb Call Setup Time M2M,MO (s) (3 Times Average) |  |  |  | 4s | 2.9/3/2.7 | 3.3/3/3.4 | 3.3/2.9/3.7 | ok
Time To Return To LTE After Csfb Call (3 Times Average) |  |  |  | 2.5s | 0.7/0.8/0.7 | 0.9/0.7/0.8 | 0.9/0.8/0.7 | ok
Data Interruption Delay Due To Csfb (3 Times Average) |  |  |  | 4s | 0.5/0.7/0.6 | 0.5/0.4/0.5 | 0.6/0.5/0.6 | ok
SMS (1 Time) |  |  |  | - | ok | ok | ok | ok
SMS Sending Time |  |  |  | - | 0.39/0.48/0.43 | 0.40/0.49/0.47 | 0.42/0.48/0.45 | ok
RSRP |  |  |  | - | -62/-67/-66 | -63/-68/-65 | -64/-66/-67 | ok
SINR |  |  |  | - | 21/25/27 | 26/29/28 | 23/24/27 | ok
RSRQ |  |  |  | - | -9/-9/-9 | -7/-8/-9 | -7/-7/-6 | ok
C-Dynamic Check
4G KPIs Drive Test |  |  | Results(OK/NOK) |  | D-OSS KPIs & Configuration check |  | Results(OK/NOK)
RSRP Distribution |  |  |  |  | 4G Parameters Setting
RSRQ Distribution
SINR Distribution |  |  |  |  | 4G OSS KPIs
PCI Distribution
Average UL/DL Throughput (>8/15 Mbps While RSRP>-102) |  |  |  |  | 2G/3G OSS KPIs (Before/After)
Csfb on Mobility & Handover
Comments :
SSV Validated Signature:
TT Optim Team |  |  | Date |  | Ericsson |  |  | Date

## LTE SSV DT PLOT
LTE SSV REPORT
RSRP L800 Plot | RSRP L1800 Plot
RSRQ L800 Plot | RSRQ L1800 Plot
SINR L800 Plot | SINR L1800 Plot
Best Server PCI Distribution L800 Plot | Best Server PCI Distribution L1800 Plot
DL THROUGHPUT L800 Plot | DL THROUGHPUT L1800 Plot
UL THROUGHPUT L800 Plot | UL THROUGHPUT L1800 Plot
Comments :

## LTE SSV DT PLOT 2100
LTE SSV REPORT
RSRP L2100 Plot
RSRQ L2100 Plot
SINR L2100 Plot
Best Server PCI Distribution L2100 Plot
DL THROUGHPUT L2100 Plot
UL THROUGHPUT L2100 Plot
Comments :

## ANNEX
ANNEX
SITE VIEW
Comment: According to the PCI distribution, the cells of “Mtir_Haouel” are no dominant. The coverage of the site is limited compared to its neighbors. In fact, the antenna height of “Mtrir_Haouel” sectors are lower than the neighbors. Need to adjust the tilt of the below sectors to clean the best servers and increase the coverage area of “Mtir_Haouel”: and that caused the degradation of KPIs
Comments :
600 m
600 m
400 m
553 m