## SSV_4G
Rollout Site ID | Region | NobeBName | 4G OSS ID | Rollout Site Name | Config | OSS/SSV | OnairDate | SSV Status | SSV Date | SSV Report Status | Comment | Number of visit
PH2_L1_C10_090 | Kairouan | 3G_SIDI_ABDALLAH | LKA062 | 3G_SIDI_ABDALLAH_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/22/2025 | Incomplete | 2025-09-03 | Incomplete | 03/09/2025: Target not reached dl (ca) on 3 sectors and dl S1 L2100 16/09/2025: Target not reached dl (ca) on 3 sectors | 2
PH2_L1_C10_094 | Kairouan | 3G_El_Khadra | LKA093 | 3G_El_Khadra_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/20/2025 | Incomplete | 2025-09-05 | Incomplete | 05/09/2025:Target not reached dl (CA) on 3 sectors 16//09/2025: Cross 800 | 2
PH2_L1_C10_001 | Gabes | 3G_Hama_sombat | LGB072 | 3G_Hama_sombat_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/26/2025 | Incomplete | 2025-09-03 | Incomplete | 03/09/2025: Target not reached DL all bands(Site not stable) | 1
PH2_L1_C10_002 | Gabes | 3G_RASZOUIE | LGB007 | 3G_RASZOUIE_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/25/2025 | Incomplete | 2025-09-03 | Incomplete | 03/09/2025:Target not reached dl (CA+1800+2100 ) on s1 and s3 due to site access problem. | 1
PH2_L1_C10_008 | Kairouan | 3G_KHAZZAZIA | LKA041 | 3G_KHAZZAZIA_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/21/2025 | Incomplete | 2025-09-05 | Incomplete | 05/09/2025:Target not reached dl (CA) on 3 sectors ( DUE to CROSS ON BAND 800) | 1
PH2_L1_C10_009 | Kairouan | 3G_OULED_BELLIL | LKA001 | 3G_OULED_BELLIL_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/26/2025 | Done | 2025-09-03 | Done |  | 1
PH2_L1_C10_011 | Kasserine | 3G_RPT_Sbitla | LKS066 | 3G_RPT_Sbitla_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/27/2025 | Incomplete | 2009-09-11 | Incomplete | 11/09/2009: cross between S2&S3 | 1
PH2_L1_C10_018 | Mahdia | 3G_OULED_CHAM2 | LMA060 | 3G_OULED_CHAM2_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/26/2025 | Done | 2009-09-12 | Done | 12/09/2009: | 1
PH2_L1_C10_020 | Mahdia | 3G_CHhimet | LMA063 | 3G_CHhimet_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/27/2025 | Done | 2009-09-12 | Done | 12/09/2009: | 1
PH2_L1_C20_001 | Kairouan | 3G_Kairouan_ZI | LKA744 | 3G_Kairouan_ZI_Add_4th_Sector | PH2-L1_C20-ADD_Sector | SSV | 8/25/2025 | Done | 2025-09-16 | Ongoing | 16/09/2025: | 2
PH2_L1_C10_034 | Monastir | 3G_bkalta_2 | LMO093 | 3G_bkalta_2_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/20/2025 | Done | 2025-08-30 | Done | 30/08/2025: | 1
PH2_L1_C10_035 | Monastir | 3G_Bkalta_dimess | LMO436 | 3G_Bkalta_dimess_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/22/2025 | Done | 2025-08-30 | Done | 18/09/2025 19/09/2025 | 2
| Monastir | 3G_Bkalta_dimess | UMO436 | 3G_Bkalta_dimess_900 |  | SSV |  | Incomplete |  | Incomplete | 18/09/2025: Circular cross U900 | 2
PH2_L1_C10_037 | Monastir | 3G_Falaise_III | LMO450 | 3G_Falaise_III_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/18/2025 | Done | 2025-09-18 | Ongoing | 18/09/2025: | 2
PH2_L1_C10_039 | Monastir | 3G_Ghdir | LMO939 | 3G_Ghdir_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/14/2025 | Done | 2025-09-09 | Done | 2025-09-09 | 1
PH2_L1_C10_040 | Monastir | 3G_Ksar_helal2_CTT | LMO086 | 3G_Ksar_helal2_CTT_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/27/2025 | Done | 2009-09-12 | Done | 2009-09-12 | 1
PH2_L1_C10_043 | Monastir | 3G_Menzel_Harb | LMO362 | 3G_Menzel_Harb_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/15/2025 | Done | 2025-08-30 | Done | 30/08/2025: | 1
PH2_L1_C10_047 | Monastir | 3G_Sayada2 | LMO078 | 3G_Sayada2_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/19/2025 | Done | 2025-08-30 | Done | 30/08/2025: | 1
PH2_L1_C10_048 | Monastir | 3G_Skanes_Beach | LMO328 | 3G_Skanes_Beach_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/15/2025 | Done | 2025-08-30 | Done | 29/08/2025: | 1
PH2_L1_C10_049 | Monastir | 3G_Tboulba_Erriadh | LMO408 | 3G_Tboulba_Erriadh_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/14/2025 | Done | 2025-09-09 | Done |  | 1
PH2_L1_C10_052 | Nabeul | 3G_El_mazraa | LNA021 | 3G_El_mazraa_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/15/2025 | Incomplete | 2025-09-04 | Incomplete | 04/09/2025:Target not reached S1,S2,S3(ca,L1800,L2100) | 2
PH2_L1_C10_059 | Nabeul | 3G_Hotel_Medi_Sea | LNA458 | 3G_Hotel_Medi_Sea_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/18/2025 | Done | 2025-08-29 | Done | 2025-08-29 | 1
PH2_L1_C10_062 | Nabeul | 3G_Rte_Sliman | LNA170 | 3G_Rte_Sliman_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/21/2025 | Done | 2025-08-29 | Ongoing | 2025-08-29 | 1
PH2_L1_C10_063 | Nabeul | 3G_SIDI_ELMAHRSI_COH | LNA413 | 3G_SIDI_ELMAHRSI_COH_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/20/2025 | Incomplete | 2025-09-05 | Incomplete | 04/09/2025:Target not reached S1,S2,S3(ca,L1800,L2100) S1 ALARME VSWR | 2
PH2_L1_C10_065 | Nabeul | 3G_AFRICA_JAD | LNA070 | 3G_AFRICA_JAD_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/14/2025 | Incomplete | 2025-09-15 | Incomplete | 15/09/2025:Static DONE (Dynamic path issue) | 1
PH2_L1_C10_067 | Sidi_Bouzid | 3G_LESSOUDA_DELICE | LSB083 | 3G_LESSOUDA_DELICE_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/26/2025 | Incomplete | 2009-09-11 | Incomplete | 11/09/2009:Target not reached dl (CA+L1800+L2100) | 1
PH2_L1_C10_071 | Sidi_Bouzid | 3G_PT_87 | LSB053 | 3G_PT_87_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/27/2025 | Incomplete | 2009-09-11 | Incomplete | 11/09/2009: Site down | 1
PH2_L1_C10_073 | Sousse | 3G_Mesaadine_II | LSO033 | 3G_Mesaadine_II_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/19/2025 | Incomplete | 2025-09-08 | Incomplete | Circular cross | 1
PH2_L1_C10_078 | Sousse | 3G_RPT_K_AKOUDA | LSO090 | 3G_RPT_K_AKOUDA_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/21/2025 | Done | 2025-08-28 | Done | 2025-08-28 | 1
PH2_L1_C10_074 | Sousse | 3G_Erriadh_III | LSO007 | 3G_Erriadh_III_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/20/2025 | Done | 2025-08-29 | Done | 2025-08-29 | 1
PH2_L1_C10_079 | Sousse | 3G_Maison_mer | LSO061 | 3G_Maison_mer_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/22/2025 | Done | 2025-08-29 | Done | 2025-08-29 | 1
PH2_L1_C10_095 | Nabeul | 3G_El_Amra | UNA071 | 3G_El_Amra_ModHB+Ext_L2100 | PH2-L1_C10-Mod_HB | SSV | 8/22/2025 | Incomplete | 2025-09-04 | Incomplete | 04/09/2025:Target not reached S1,S2,S3(ca,L1800,L2100) | 2
PO3_L1_C5_001 | Tataouine | 3G_MAOUNA_III_Ext4G+Mod2G3G |  |  | PO3-L1_C05-Mod_HB | SSV |  | Done | 2025-09-05 | Done | 2025-09-05 | 1
PO3_L3_C5_017 | Tataouine | 3G_Jbel_Angar_Ext4G+Mod2G3G_2T2R |  |  | PO3-L1_C05-Mod_HB | SSV |  | Incomplete | 2025-09-05 | Incomplete | 05/09/2025:Access to S2 is unavailable due to it being in a military zone S1,S3: done | 1
PO3_L1_C12_007 | Gabes | 3G_Sih_Amara | UGB076 |  | PO3-L3_C08-Mod_HB | SSV |  | Done | 2025-09-02 | Done | 2025-09-02 | 1
PO3_L3_C8_005 | Sousse | B4G_Micro_Ezzayet_Msaken1 | LSO794 |  |  | SSV |  | Done | 2009-09-12 | Ongoing | 12/09/2009: | 1
PO3_L3_C8_005 | Sousse | B4G_Micro_Ezzayet_Msaken2 | LSO894 |  |  | SSV |  | Done | 2009-09-12 | Done | 12/09/2009: | 1
PO3_L3_C5_001 | Kairouan | RACADA_MUSE | LKA029 | 3G_RACADA_MUSE_Ext4G+Mod2G3G_2T2R |  | SSV |  | Done | 2025-09-19 | Ongoing | 19/09/2025: | 1
PO3_L3_C4_005 | Sousse | 3G_CTT_Thrayet | LSO894 | 3G_CTT_Thrayet_Ext4G+Mod2G3G_4T4R |  | SSV |  | Incomplete | 2009-09-19 | Incomplete | 19/09/2009:Target not reached S1,S3 DL (1800,ca) | 1